# Pharmacy Online Store & Order Management System — Project Planning & Management

## 1. Project Proposal

### A. Project Overview

The Pharmacy Online Store & Order Management System is a responsive web application designed for a single retail pharmacy. The system bridges the digital gap between retail customers and physical pharmacy operations by providing a web-based storefront, digital prescription intake, order tracking, and a dedicated back-office management suite.

The software addresses operational bottlenecks caused by manual telephone or messaging order intake and provides structured workflows for order fulfillment, prescription handling, product requests, and local delivery. The application serves four primary roles: Customer, Pharmacist, Driver, and Admin. The Pharmacy Owner accesses system functionality using an Admin account as a business stakeholder.

### B. Project Objectives

- Customer Accessibility: Enable retail customers to browse products, place regular orders, upload prescription images, and request unlisted products via a responsive interface.

- Streamlined Prescription Review: Digitize the prescription submission and pharmacist review workflow, eliminating manual clarification back-and-forth and removing unnecessary post-submission customer approvals.

- Operational Order & Delivery Tracking: Provide centralized dashboards for pharmacy staff to process orders, assign driver routes, track two-attempt delivery outcomes, and log Cash on Delivery (COD) collections.

- Efficiency & Delay Reduction: Capture customer preferences for unavailable products upfront to prevent order stagnation and eliminate avoidable back-and-forth interactions.

- Centralized Administration & Oversight: Provide management with centralized catalog administration, user access control, and operational reporting without replacing existing pharmacy ERP/POS infrastructure.

### C. Project Scope

#### In Scope (Release 1.0)

- Responsive customer storefront (browse, search, cart, checkout with COD).

- Customer registration, authentication, address book, and account management.

- Upfront selection of customer preferences for unavailable products during regular checkout (Provide Alternative, Remove Item, Cancel Order).

- Prescription upload and mandatory review workflow (single submission by customer, pharmacist product/quantity attachment, direct order confirmation).

- Product request submission form for items missing from the store catalog.

- Staff dashboards for Admin, Pharmacist, and Driver roles.

- Manual product availability toggling (Available / Unavailable).

- Order lifecycle management, driver assignment, two-attempt delivery tracking, and COD amount recording.

- In-website event notifications for order status updates.

- Administrative reporting on sales, order volumes, and delivery outcomes.

#### Out of Scope (Explicitly Excluded)

- Inventory management (numerical stock tracking, automatic deduction, stock reservations, batch/expiry tracking, or stock movement ledgers).

- Online payment processing gateways (COD is the sole payment method).

- Multi-branch or multi-tenant management.

- Integration with external ERP, POS, or inventory systems.

- Third-party delivery provider API integration.

- SMS or WhatsApp notification services.

- Post-review customer approval or offer-acceptance stages for prescription orders.

### D. Expected Outcomes

- Reduced Order Processing Time: Faster turnaround for prescription and regular orders through structured staff queues.

- Lower Order Cancellation Rates: Reduction in dropped orders by capturing unavailable-item preferences upfront during checkout.

- Improved Fulfillment Accuracy: Elimination of manual pricing errors through single-source catalog price calculation post-pharmacist review.

- Full Delivery Accountability: Accurate tracking of cash collections and clear status tracking for failed delivery re-attempts.

### E. Assumptions and Constraints

- Fixed Schedule Constraint: The project must be fully completed, tested, and handed over within exactly 8 weeks.

- Fixed Resource Constraint: The project execution team consists of exactly 6 members, specifically allocated as 2 Frontend Developers and 4 Backend Developers. Additional project responsibilities (PM, UI/UX, QA, DevOps) are distributed among these 6 technical members.

- Single-Pharmacy Operations: The deployment targets one physical pharmacy location with COD-only transactions.

- No Inventory Logic: System availability relies entirely on manual staff toggles; numerical stock synchronization is out of scope.

- Prescription Workflow Rules: Customers submit prescriptions once without viewing prices; pharmacists determine items and confirm the order directly; no post-review customer re-confirmation exists.

## 2. Project Plan — Fixed Eight-Week Schedule

### A. Milestones

| Milestone ID | Milestone Name | Target Week | Acceptance Condition | Responsible Member |
| --- | --- | --- | --- | --- |
| MS-01 | Requirements Approved | Week 1 | Functional requirements, business rules, scope exclusions, and acceptance criteria validated and signed off. | Member 3 |
| MS-02 | UI/UX & System Planning Completed | Week 2 | Interactive UI wireframes, relational data schema, and API specifications formally reviewed and approved. | Member 1 & 4 |
| MS-03 | Core Backend Features Completed | Week 3 | User authentication, RBAC authorization, and catalog management endpoints deployed and verified via API tests. | Member 3 |
| MS-04 | Main Business Workflows Completed | Week 4 | Regular order logic, prescription handling, unavailable item options, and product request engines operational on backend. | Member 4 |
| MS-05 | Frontend & Backend Integration Completed | Week 6 | Customer storefront and all staff dashboards connected to backend APIs; end-to-end data flow verified across all roles. | Member 2 |
| MS-06 | Testing Completed | Week 7 | Functional, RBAC security, prescription workflow, and delivery regression tests executed; 0 critical/high bugs remaining. | Member 6 |
| MS-07 | Final Delivery & Handover Completed | Week 8 | Application deployed to production environment, operational documentation delivered, and system signed off. | Member 3 |

### B. Deliverables

- Week 1: Validated Business Requirements Document, Scope Traceability Matrix, Acceptance Criteria Specification.

- Week 2: High-Fidelity UI/UX Screen Mockups, System Data Models, API Interface Contract Specifications.

- Week 3: Functional Backend Core (Auth, User Security Roles, Product Catalog & Category APIs).

- Week 4: Business Logic Engine (Order Checkout APIs, Unavailable Product Preference Handlers, Prescription Intake & Review Modules).

- Week 5: Delivery Module Backend, COD Logging Engine, In-App Notification Hub, Customer Storefront Web Interface.

- Week 6: Integrated Application (Admin, Pharmacist, Driver Dashboards wired to Backend Data Services).

- Week 7: QA Test Execution Suite, Test Summary Report, Defect Remediation Log, Security Access Audit.

- Week 8: Production Release Deployment, System Administration & Operational Manual, Final Project Handover Document.

### C. Dependencies and Parallel Work

- Design & Architecture Parallelism (Week 2): UI/UX screen design (Member 1) runs concurrently with Database & API contract modeling (Members 3 & 4).

- Heavy Backend Parallelism (Weeks 3–5): With 4 backend developers, the API and database workload is heavily parallelized. While Auth/Catalog is built, Order logic and Delivery/Notification systems are constructed simultaneously.

- Frontend Split (Weeks 5–6): Member 1 develops the customer storefront while Member 2 simultaneously builds the staff dashboards.

- Testing Preparation (Week 6): QA test case design (Member 6) begins during the frontend completion phase, ensuring execution starts immediately once integration finishes at the end of Week 6.

### D. Schedule Assumptions

- Team Availability: All 6 team members are available for full-time project allocation (assumed 40 hours/week) for the entire 8-week duration.

- Distributed Responsibilities: Because the team composition is fixed at 2 Frontend and 4 Backend developers, non-development roles (PM, BA, QA, UI/UX, Deployment) are absorbed by these developers according to their task assignments.

- Schedule Constraint: The 8-week timeline is fixed. If technical blockers arise, the heavy backend capacity (4 developers) will be leveraged to unblock APIs faster, ensuring the frontend developers (2 developers) are never waiting for endpoints.

## 3. Task Assignment & Roles — Exactly Six Team Members

### Baseline Role Allocation

To meet project needs with the specific 2 Frontend / 4 Backend team composition, responsibilities are distributed as follows:

| Member | Project Role | Primary Responsibilities |
| --- | --- | --- |
| Member 1 | Frontend Developer 1 (UI/UX & Storefront) | Design user flows and interfaces, implement responsive customer-facing screens, and maintain usability and visual consistency. |
| Member 2 | Frontend Developer 2 (Dashboards & Integration) | Implement Admin, Pharmacist, and Driver dashboards, handle API wiring, and support overall frontend/backend integration. |
| Member 3 | Backend Developer 1 (PM, BA & Core Data) | Coordinate the team, manage schedule/requirements (PM/BA), implement authentication, RBAC, and catalog backend APIs. |
| Member 4 | Backend Developer 2 (Order & Rx Workflows) | Design system data models, implement regular order processing, prescription review logic, and unavailable-product handlers. |
| Member 5 | Backend Developer 3 (Delivery & Notifications) | Implement delivery assignment logic, COD recording APIs, in-website notifications, and product request endpoints. |
| Member 6 | Backend Developer 4 (QA & Deployment) | Prepare test cases, validate business workflows, report defects, execute security testing, and handle server deployment/handover. |

(Note: These are project execution roles. The application's four user roles remain Admin, Pharmacist, Driver, and Customer).

### A. Detailed Task Assignment

| Task ID | Task Name | Primary Owner | Supporting Members | Start Week | End Week | Duration | Dependencies | Expected Deliverable |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T01 | Requirements Validation & Scope Baseline | Member 3 | M1, M2, M4, M5, M6 | Week 1 | Week 1 | 1 Wk | None | Approved Requirements Document |
| T02 | UI/UX Screen Wireframing & Design | Member 1 | Member 2 | Week 2 | Week 2 | 1 Wk | T01 | UI/UX Designs & Assets |
| T03 | Data Modeling & API Contract Design | Member 4 | Member 3, Member 5 | Week 2 | Week 2 | 1 Wk | T01 | System Design & API Docs |
| T04 | Authentication, RBAC & User Management | Member 3 | Member 6 | Week 3 | Week 3 | 1 Wk | T03 | Core Backend Functionality |
| T05 | Product Catalog & Category Management | Member 3 | Member 4 | Week 3 | Week 3 | 1 Wk | T03 | Catalog Endpoints |
| T06 | Regular Order & Unavailable Product Logic | Member 4 | Member 5 | Week 4 | Week 4 | 1 Wk | T04, T05 | Regular Order Workflows |
| T07 | Prescription Intake & Pharmacist Review Logic | Member 4 | Member 3 | Week 4 | Week 4 | 1 Wk | T04, T05 | Prescription Workflows |
| T08 | Product Request Submission Engine | Member 5 | Member 4 | Week 4 | Week 4 | 1 Wk | T04, T05 | Product Request APIs |
| T09 | Delivery Assignment, COD & Notifications BE | Member 5 | Member 6 | Week 5 | Week 5 | 1 Wk | T06 | Delivery & Notification APIs |
| T10 | Storefront Browsing, Cart & Checkout FE | Member 1 | Member 2 | Week 5 | Week 5 | 1 Wk | T02, T06 | Customer-Facing Screens |
| T11 | Admin, Pharmacist & Driver Dashboards FE | Member 2 | Member 1 | Week 6 | Week 6 | 1 Wk | T02, T09 | Staff Dashboards |
| T12 | Full System Integration & API Wiring | Member 2 | M1, M3, M4, M5 | Week 6 | Week 6 | 1 Wk | T10, T11 | Integrated Application |
| T13 | Test Case Preparation & Execution | Member 6 | Member 3 | Week 6 | Week 7 | 2 Wks | T12 | Test Report |
| T14 | Integration, Security & Workflow Bug Fixing | Member 6 | M1, M2, M3, M4, M5 | Week 7 | Week 7 | 1 Wk | T13 | Resolved Defects |
| T15 | Final Acceptance Testing & Production Deploy | Member 6 | Member 3, Member 5 | Week 8 | Week 8 | 1 Wk | T14 | Release-Ready System |
| T16 | System Documentation & Final Handover | Member 3 | M1, M2, M4, M5, M6 | Week 8 | Week 8 | 1 Wk | T15 | Handover Package |

### B. Workload and Collaboration

- Project Management Oversight: Member 3 manages the schedule, risks, and requirements documentation in Week 1 and Week 8, while focusing on foundational backend code during Weeks 3 and 4.

- Frontend Coordination: Member 1 and Member 2 split the UI workload perfectly. Member 1 handles all customer-facing design and development, while Member 2 tackles the complex, multi-role staff dashboards.

- Backend Distribution: With 4 backend developers, the load is distributed by domain. Member 3 handles Auth/Catalog; Member 4 handles the critical Order/Prescription logic; Member 5 handles the trailing workflows (Delivery/Notifications); Member 6 transitions early into QA automation and deployment architecture.

- QA & Integration Integration: Member 6 prepares test cases in Week 6 while Member 2 leads the API wiring. During Week 7, Member 6 tracks all defects, while Members 1-5 remediate bugs in their respective domains.

### C. Responsibility Matrix

| Major Project Activity | M1 (FE 1) | M2 (FE 2) | M3 (BE 1) | M4 (BE 2) | M5 (BE 3) | M6 (BE 4) |
| --- | --- | --- | --- | --- | --- | --- |
| Project Management & Requirements | S | S | P | S | S | S |
| UI/UX Screen Mockups & Design | P | S | - | - | - | - |
| Data Schema & API Contract Design | - | - | S | P | S | - |
| Auth, RBAC & Catalog Development | - | - | P | S | - | S |
| Orders & Prescription Logic Engine | - | - | S | P | S | - |
| Delivery, COD & Notification Engine | - | - | - | S | P | S |
| Customer Storefront Frontend | P | S | - | - | - | - |
| Staff Dashboards (Admin, Rx, Driver) | S | P | - | - | - | - |
| End-to-End System Integration | S | P | S | S | S | - |
| QA Test Execution & Defect Verification | - | - | S | - | - | P |
| Code Defect Remediation | S | S | S | S | S | P |
| Production Deployment & Handover | S | S | P | S | S | P |

(Legend: P = Primary Owner, S = Supporting Member, - = No Direct Involvement)

## 4. Risk Assessment & Mitigation Plan

| Risk ID | Risk Description | Prob. | Impact | Mitigation Strategy | Contingency Plan | Responsible Member |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Delayed Stakeholder Approval: Requirements or UI designs take too long to approve, threatening the 8-week timeline. | Medium | High | Conduct daily reviews in Weeks 1 & 2. Set strict 24-hour turnaround expectations. | Proceed with development using the documented baseline; defer feedback to post-launch. | Member 3 |
| R-02 | Prescription Workflow Misinterpretation: Developers add post-review customer approvals or price acceptance steps. | Medium | High | Explicitly document the single-submission rule in API contracts during Week 2. | Immediately refactor workflow logic during Week 4 to enforce single customer submission. | Member 4 |
| R-03 | Frontend/Backend Integration Delays: Mismatched data structures slow down integration in Week 6. | High | Medium | Lock OpenAPI/Swagger interface definitions in Week 2. Enforce strict adherence by all 4 backend devs. | Member 2 and Member 4 pair-program to manually resolve contract mismatches. | Member 2 |
| R-04 | Delivery Attempt & COD Tracking Failures: Drivers encounter UI issues when updating statuses or logging cash. | Medium | Medium | Member 1 focuses heavily on mobile-responsive touch targets for the Driver Dashboard. | Admin manually adjusts statuses based on physical driver logs until a UI patch is pushed. | Member 1 |
| R-05 | Miscalculation in COD Order Totals: Final totals fail to update correctly when unavailable items are removed. | Low | High | Member 6 writes automated backend unit tests for pricing logic in Week 6. | Member 4 halts feature work to remediate calculation bugs during QA execution. | Member 4 |
| R-06 | Unauthorized Access to Sensitive Data: Prescription images or customer info is exposed due to poor RBAC. | Low | High | Member 3 builds strict, role-based middleware. Drivers are explicitly denied Rx image access. | Revoke access tokens, patch middleware, and notify stakeholders immediately. | Member 3 |
| R-07 | Frontend Bottleneck: With only 2 FE devs and 4 BE devs, frontend UI development falls behind API completion. | High | High | M3, M4, and M5 provide comprehensive, mocked API data early so M1 and M2 can build UI without waiting. | Delay non-critical dashboard views (e.g., historical reporting) to ensure core workflows ship. | Member 3 |
| R-08 | Deployment or Configuration Problems: Errors occur during the final move to production in Week 8. | Low | High | Member 6 prepares staging environments and CI/CD pipelines early in Week 7. | Revert to stable staging build; delay final handover by 24 hours to resolve config errors. | Member 6 |